## Slide 1
TOURGUIDE
Software Project Management — Lab Journey & Final Evaluation
Abdullah
Roll No: 47168 | abiezofficial@gmail.com
Ahmed Zia
Roll No: 54635 | azia18966@gmail.com

## Slide 2
OVERVIEW
Lab Journey — 12 Labs
1. Project Initialization
2. Time Planning (Gantt)
3. Initiation & Planning Doc
4. MS Project
5. MS Planner
6. Taiga (Scrum/Kanban)
7. Work Breakdown Structure
8. Network Diagram & CPM
9. GitHub Fundamentals
10. Cost Estimation (COCOMO)
11. GitHub Workflow & Collaboration
12. Final Evaluation

## Slide 3
LAB 1
Project Initialization
Project: TourGuide — Trip Booking Web App
Problem Statement
Tourists rely on scattered sources for trip research and booking — no unified platform with gallery, booking, and direct contact in one place.
Stakeholders
Tourists, Admin, Dev Team, Supervisor
Team
Name | Role
Abdullah | Project Lead / Full-Stack Dev
Ahmed Zia | Frontend Dev / Documentation
Expected Improvement
Centralized booking, instant confirmation, full admin CRUD control — replacing manual, fragmented processes.

## Slide 4
LAB 2
Time Planning — Gantt Chart
Task | Duration
Project Charter | 5 days
Feasibility Study | 7 days
Requirement Analysis | 14 days
System Design | 9 days
Development | 14 days
Testing | 16 days
Deployment | 18 days
Project Charter
Feasibility Study
Requirement Analysis
System Design
Development
Testing
Deployment
End Date = Start Date + Duration (live formula, zero hardcoded values)

## Slide 5
LAB 3
Project Initiation & Planning
Feasibility
Technical, Economic, Operational — all confirmed viable
Resources
2-member team, MERN stack, free-tier hosting
Cost & Risk
~PKR 8-10K budget; key risks: schedule delays, scope creep
Team & RACI
Abdullah (PM/Backend), Ahmed Zia (Frontend/Docs)
Rollout Plan
Phased deployment — backend first, then frontend integration

## Slide 6
LAB 4
MS Project — Task Scheduling
Tasks entered, indented into phases, and linked with Finish-to-Start dependencies. Gantt chart auto-generated in MS Project.
📷 SCREENSHOT
MS Project view — task list + Gantt chart (left + right pane)

## Slide 7
LAB 5
MS Planner — Task Boards
TourGuide tasks organized into buckets with assignees, due dates, and progress tracking.
📷 SCREENSHOT
MS Planner board — buckets and task cards

## Slide 8
LAB 6
Taiga — Scrum & Kanban
Jira Scrum board: 2 sprints, 24+ user stories. Taiga Kanban tracking parallel workflow.
📷 SCREENSHOT
Jira Scrum board (sprints/stories)
📷 SCREENSHOT
Taiga Kanban board

## Slide 9
LAB 7
Work Breakdown Structure
TourGuide
Tourist Module
Login/Register
Browse Destinations
Booking Module
Trip Selection
Confirmation
Payment
Gallery Module
Upload (Admin)
Display (Tourist)
Contact Module
Form Submit
Query Storage
Admin Panel
Destination CRUD
Booking Mgmt
Gallery CRUD

## Slide 10
LAB 8
Network Diagram & CPM
Activity | Description | Dur | EST | EFT | LST | LFT | Slack
A | Requirement Gathering | 3 | 0 | 3 | 0 | 3 | 0
B | Feasibility Study | 2 | 3 | 5 | 3 | 5 | 0
C | System Design | 5 | 5 | 10 | 5 | 10 | 0
D | Backend Setup | 4 | 5 | 9 | 7 | 11 | 2
E | Frontend Dev | 6 | 10 | 16 | 10 | 16 | 0
F | Backend Integration | 5 | 9 | 14 | 11 | 16 | 2
G | Integration & Testing | 4 | 16 | 20 | 16 | 20 | 0
H | Deployment | 2 | 20 | 22 | 20 | 22 | 0
Critical Path: A → B → C → E → G → H Total Duration: 22 Days

## Slide 11
LAB 9
Git & GitHub Fundamentals
Individual repository practice — staging, commits, branching, merging, and commit history.
📷 SCREENSHOT
Commit history (git log)
📷 SCREENSHOT
Branch merge confirmation

## Slide 12
LAB 10
Cost Estimation — COCOMO
8500
Total LOC
8.5
KLOC
122
Function Points
22.7
Person-Months
Formula:
Effort = 2.4 × (KLOC)^1.05 = 2.4 × (8.5)^1.05 ≈ 22.7 Person-Months
Note: COCOMO assumes industrial team scale. Actual TourGuide delivery (per Gantt chart) was ~3 months with a 2-person team — this figure is a theoretical academic benchmark, not literal effort spent.

## Slide 13
LAB 11
Advanced GitHub Workflow
TourGuide repo: branching strategy, issues, pull requests, merge conflict resolution, project board, and v1.0.0 release.
📷 SCREENSHOT
Branching structure (main/dev/feature)
📷 SCREENSHOT
Issues list (5 issues)
📷 SCREENSHOT
Pull Request + review comment
📷 SCREENSHOT
Merge conflict resolution
📷 SCREENSHOT
Project board (Kanban)
📷 SCREENSHOT
Release v1.0.0

## Slide 14
SUMMARY
Tools & Techniques Applied
Planning
Excel Gantt, MS Project, MS Planner
Agile Mgmt
Jira, Taiga (Scrum/Kanban)
Scheduling
Network Diagram, CPM
Estimation
LOC, Function Points, COCOMO
Version Control
Git, GitHub (branching, PRs, releases)
Documentation
WBS, RACI, Risk Register

## Slide 15
Thank You
TourGuide — from problem statement to deployment-ready release
Questions?