Software Project Management

PBL

Submitted by:

Ahmad Zia

M. Abdullah

SAP ID: 54635

47618

BSSE 6

Project Title:

Tourguide

.

# Lab:1

# 1. Formation of Project Groups

## 1.1 Group Details

| Field | Details |
| --- | --- |
| Member 1 Name | Ahmad Zia |
| Member 1 Roll No. | 54635 |
| Member 1 Role | Team Leader & Full Stack Developer |
| Member 2 Name | Abdullah |
| Member 2 Roll No. | 47618 |
| Member 2 Role | Documentation Coordinator |

## 1.2 Role Descriptions

### Team Leader & Full Stack Developer (Ahmad Zia)

Responsible for project planning, task allocation, frontend and backend development, database integration, and ensuring timely completion of project deliverables.

### Documentation Coordinator (Abdullah)

Responsible for preparing project reports, maintaining documentation, updating project records, and assisting in requirement analysis.

# 2.  Selection of Software Project

## 2.1 Project Title

### Tour Guide Application – Web Based Tour Booking System

## 2.2 Project Overview

Tour Guide Application is a web-based platform developed to simplify tour package booking and management. The system consists of two user roles: Customers and Administrators.

Customers can create accounts, login securely, browse tour packages, book trips, manage carts, upload travel photos, submit ratings, and send queries to administrators.

Administrators can manage tour packages, monitor customer activities, review submitted queries, and mark resolved issues through an administrative dashboard.

The application provides a centralized and user-friendly environment for travelers and tourism companies.

## 2.3 Project Objectives

• Provide an online platform for browsing tour packages.

• Allow customers to register and login securely.

• Enable customers to book tours and manage carts.

• Provide package pricing calculations.

• Allow customers to upload travel images.

• Enable customers to submit ratings.

• Facilitate customer query submission.

• Provide an admin dashboard.

• Allow administrators to perform CRUD operations on packages.

• Enable administrators to manage customer queries.

# 3. Identification of Stakeholders

## 3.1 Stakeholder Categories

| Stakeholder Category | Role | Interest Level |
| --- | --- | --- |
| Tourism Company | Client | High |
| Customers | End Users | High |
| Project Manager | Supervision | High |
| Developers | System Development | Medium |
| Testers | Quality Assurance | Medium |
| Administrator | System Management | High |
| Hosting Provider | Infrastructure | Medium |

## 3.2 Stakeholder Interest Description

### Primary Stakeholders

Customers are the primary users of the system. Their satisfaction directly determines project success.

The Tourism Company acts as the client and defines business requirements.

### Secondary Stakeholders

Developers implement the software features.

Testers validate application quality.

Project Manager oversees project progress.

### External Stakeholders

Hosting providers ensure application availability and deployment support.

# 4. Problem Statement Definition

## 4.1 Current Issues

• Customers depend on phone calls or physical visits to book tour packages.

• Traditional booking methods are slow and inconvenient.

• Customers cannot easily compare available packages.

• Feedback collection is mostly manual.

• Customer queries are not centrally managed.

• Package information updates require significant manual effort.

## 4.2 Limitations of Manual Processes

• Booking procedures consume considerable time.

• Manual record keeping increases chances of errors.

• Customer feedback and travel galleries cannot be efficiently maintained.

• Administrators face difficulties in managing package information.

## 4.3 Expected Improvements Through Automation

• Customers can browse and book packages anytime.

• Cart functionality provides transparent pricing.

• Travel photos and ratings enhance customer engagement.

• Query submission improves communication.

• Admin dashboard simplifies package management.

• CRUD operations reduce administrative workload.

• Centralized data storage improves system efficiency.

## 4.4 Problem Statement Summary

Travelers often experience difficulties in finding suitable tour packages, booking tours, sharing travel experiences, and communicating with tourism companies. Existing manual processes are time-consuming, inefficient, and lack centralized management.

The Tour Guide Application addresses these issues by providing a web-based platform that enables customers to browse packages, manage bookings, upload images, submit ratings, and communicate through queries. Administrators can efficiently manage packages and customer interactions through a dedicated dashboard, resulting in improved customer satisfaction and operational efficiency.

# Lab:2

# 1. Gantt Chart in MS Excel

# Lab 3:

# 1. Project Description

### Problem Statement

Tourists often face difficulties in finding suitable tour packages, booking tours, sharing experiences, and communicating with tour operators. Traditional booking methods are time-consuming and inefficient. A centralized system is needed to simplify package browsing, booking, feedback, and customer support.

### Project Objectives

- Provide an online platform for tour package booking.

- Allow customers to browse and book tour packages.

- Enable customers to manage their cart and view total costs.

- Allow customers to upload travel images and ratings.

- Facilitate customer query submission.

- Provide an admin panel for package and query management.

### Brief System Overview

The Tour Guide Application is a web-based system consisting of two user roles: Admin and Customer. Customers can register, login, browse packages, book tours, manage carts, upload gallery images, submit ratings, and send queries. Admins can manage tour packages, handle customer queries, and monitor system activities.

### Stakeholders

| Stakeholder | Role |
| --- | --- |
| Client | Tourism Company |
| Customers | End Users |
| Project Manager | Project Supervision |
| Developers | System Development |
| Tester | Quality Assurance |
| Admin | System Management |

# 2. Feasibility Analysis

## Technical Feasibility

### Required Technologies

- React.js

- Node.js

- Express.js

- MongoDB

- HTML

- CSS

- JavaScript

### Tools/Platforms

- Visual Studio Code

- MongoDB Atlas

- GitHub

- Postman

### Conclusion

The required technologies are widely available and team members possess the necessary skills.

## Economic Feasibility

### Estimated Cost

| Item | Cost (PKR) |
| --- | --- |
| Development Tools | 10,000 |
| Hosting | 15,000 |
| Domain | 5,000 |
| Testing | 10,000 |
| Miscellaneous | 10,000 |
| Total | 50,000 |

### Expected Benefits

- Faster booking process

- Increased customer satisfaction

- Reduced manual work

- Better package management

## Operational Feasibility

### User Acceptance

The system is easy to use and user-friendly.

### Organizational Support

The tourism company supports digital transformation and online booking systems.

# 3. Resource Planning

## Resource Allocation Table

| Resource Type | Resource | Quantity |
| --- | --- | --- |
| Human | Project Manager | 1 |
| Human | Developers | 2 |
| Human | Tester | 1 |
| Human | Documentation Lead | 1 |
| Hardware | Laptop | 5 |
| Software | VS Code | 5 |
| Software | MongoDB Atlas | 1 |
| Financial | Budget | PKR 50,000 |

### Resource Utilization Strategy

- Developers handle coding.

- Tester performs system testing.

- Documentation Lead prepares reports.

- Project Manager monitors progress.

# 4. Time Planning

## Activity Table

| Activity | Duration (Days) | Dependency |
| --- | --- | --- |
| Requirement Gathering | 3 | None |
| Feasibility Study | 2 | Requirements |
| System Design | 5 | Feasibility |
| Database Design | 3 | Design |
| Frontend Development | 10 | Design |
| Backend Development | 10 | Database |
| Integration | 4 | Frontend & Backend |
| Testing | 5 | Integration |
| Documentation | 4 | Testing |
| Deployment | 2 | Documentation |

### Project Duration

48 Days

### Gantt Chart (Simple)

# 5. Cost Planning

## Cost Estimation Sheet

| Resource | Cost (PKR) |
| --- | --- |
| Project Manager | 15,000 |
| Developers | 20,000 |
| Tester | 5,000 |
| Documentation | 3,000 |
| Hosting | 5,000 |
| Domain | 2,000 |
| Total Budget | 50,000 |

## Cost-Benefit Analysis

### Costs

- Development Cost = PKR 50,000

### Benefits

- Automated booking system

- Improved customer service

- Better management efficiency

# 6. Team Planning

## Team Structure

### Project Manager

- Ahmad Zia

### Developers

- Developer 1

- Developer 2

### Tester

- Tester 1

### Documentation Lead

- Documentation Lead 1

## Responsibilities

| Role | Responsibility |
| --- | --- |
| Project Manager | Planning & Monitoring |
| Developers | Coding |
| Tester | Testing |
| Documentation Lead | Reports & Documentation |

# 7. Risk Planning

## Risk Register

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Requirement Changes | High | High | Regular Meetings |
| Schedule Delay | Medium | High | Buffer Time |
| Resource Unavailability | Medium | Medium | Backup Resources |
| Technical Issues | Medium | High | Technical Support |
| Database Failure | Low | High | Regular Backups |

# 8. Monitoring & Control Planning

### Monitoring Frequency

- Weekly

### Performance Indicators

| Indicator | Measurement |
| --- | --- |
| Schedule Progress | Task Completion % |
| Cost Usage | Budget Consumed |
| Defects | Number of Bugs |
| Productivity | Tasks Completed |

### Reporting Mechanism

- Weekly Status Reports

- Progress Meetings

- Project Dashboard Updates

# 9. Communication & Meeting Planning

## Communication Methods

| Method | Purpose |
| --- | --- |
| Meetings | Progress Discussion |
| Email | Formal Communication |
| WhatsApp | Quick Updates |
| Reports | Project Tracking |

## Meeting Plan

| Meeting Type | Frequency | Participants | Agenda |
| --- | --- | --- | --- |
| Team Meeting | Weekly | Team Members | Progress Review |
| Client Meeting | Bi-Weekly | Client & PM | Requirement Updates |
| Risk Meeting | Monthly | PM & Team | Risk Review |

# 10. Change Management Planning

## Change Request Process

- Submit Change Request

- Analyze Impact

- Review by Project Manager

- Approve/Reject Change

- Implement Approved Change

### Impact Analysis

| Area | Impact |
| --- | --- |
| Scope | New Features |
| Schedule | Increased Time |
| Cost | Additional Budget |

### Approval Authority

Project Manager

### Change Request Template

Field

Request ID

Date

Requested By

Description

Impact

Approval Status

# 11. RACI Matrix

| Task | PM | Developer | Tester | Client |
| --- | --- | --- | --- | --- |
| Requirement Gathering | A | C | I | R |
| System Design | A | R | I | C |
| Development | A | R | I | I |
| Testing | C | C | R | I |
| Deployment | A | R | C | I |
| Documentation | A | C | C | I |

R = Responsible
A = Accountable
C = Consulted
I = Informed

# 12. Rollout Planning

## Deployment Strategy

- Deploy on cloud hosting platform.

- Connect MongoDB Atlas database.

- Perform final testing before release.

## Production Environment Readiness

- Server configured.

- Database connected.

- Security checks completed.

## User Training Plan

- Provide user manual.

- Conduct demonstration session.

- Provide video tutorials.

## Acceptance Criteria

- User registration works correctly.

- Login validation works.

- Package booking works.

- Cart management functions properly.

- Admin CRUD operations work.

- Query management works.

- System passes all test cases.

# Lab 4:

# 1 .MS Project:

# Lab 5:

1 .Project Planner:

# Lab 6:

1 .Taiga Project Management Tool:

# LAB 7

# 1. Work Breakdown Structure (WBS):

## Introduction

The Tour Guide Application is a web-based platform that allows customers to browse and book tour packages online. The system provides features such as package booking, cart management, ratings, gallery uploads, and customer query submission. Administrators can manage tour packages, view customer queries, and monitor system activities.

The Work Breakdown Structure (WBS) decomposes the project into smaller manageable components for better planning, scheduling, estimation, and project control.

# 1.1. Tree Structure (Text-Based WBS)

◼ Tour Guide Application

▸ Authentication Module
• Welcome Screen
- Customer Button
- Admin Button
• Login System
- Login
- Validation
• Registration System
- Customer Registration
- Form Validation
• Logout System

▸ Customer Module
• Package Browsing
- View Packages
- Package Details
• Package Booking
- Select Package
- Confirm Booking
• Cart Management
- Add to Cart
- Update Cart
- Remove Package
- Total Price Calculation

▸ Feedback & Gallery Module
• Rating System
- Submit Rating
- View Ratings
• Gallery System
- Upload Image
- View Gallery

▸ Query Management Module
• Query Submission
- Submit Query
- Store Query Information
• Query Tracking
• Query Status

▸ Admin Module
• Admin Dashboard
- Activity Monitoring
• Package Management
- Add Package
- Update Package
- Delete Package
• Query Management
- View Queries
- Mark Query Resolved

▸ Database Management
• User Database
• Package Database
• Booking Database
• Query Database

# 1.2. Hierarchical Diagram Structure (Text Form)

Tour Guide Application

├── Authentication Module
│ ├── Welcome Screen
│ │ ├── Customer Button
│ │ └── Admin Button
│ ├── Login System
│ │ ├── Login
│ │ └── Validation
│ ├── Registration System
│ │ ├── Customer Registration
│ │ └── Form Validation
│ └── Logout System
│
├── Customer Module
│ ├── Package Browsing
│ │ ├── View Packages
│ │ └── Package Details
│ ├── Package Booking
│ │ ├── Select Package
│ │ └── Confirm Booking
│ └── Cart Management
│ ├── Add To Cart
│ ├── Update Cart
│ ├── Remove Package
│ └── Total Price Calculation
│
├── Feedback & Gallery Module
│ ├── Rating System
│ │ ├── Submit Rating
│ │ └── View Ratings
│ └── Gallery System
│ ├── Upload Image
│ └── View Gallery
│
├── Query Management Module
│ ├── Query Submission
│ │ ├── Submit Query
│ │ └── Store Query Information
│ ├── Query Tracking
│ └── Query Status
│
├── Admin Module
│ ├── Admin Dashboard
│ │ └── Activity Monitoring
│ ├── Package Management
│ │ ├── Add Package
│ │ ├── Update Package
│ │ └── Delete Package
│ └── Query Management
│ ├── View Queries
│ └── Mark Query Resolved
│
└── Database Management
├── User Database
├── Package Database
├── Booking Database
└── Query Database

# 2. WBS Diagram (Level-Wise Structure)

# LEVEL 0

# Tour Guide Application

# ├── LEVEL 1: Authentication Module

# │   ├── LEVEL 2: Welcome Screen

# │   │   ├── LEVEL 3: Customer Button

# │   │   └── LEVEL 3: Admin Button

# │   │

# │   ├── LEVEL 2: Login System

# │   │   ├── LEVEL 3: Login

# │   │   └── LEVEL 3: Validation

# │   │

# │   ├── LEVEL 2: Registration System

# │   │   ├── LEVEL 3: Customer Registration

# │   │   └── LEVEL 3: Form Validation

# │   │

# │   └── LEVEL 2: Logout System

# ├── LEVEL 1: Customer Module

# │   ├── LEVEL 2: Package Browsing

# │   │   ├── LEVEL 3: View Packages

# │   │   └── LEVEL 3: Package Details

# │   │

# │   ├── LEVEL 2: Package Booking

# │   │   ├── LEVEL 3: Select Package

# │   │   └── LEVEL 3: Confirm Booking

# │   │

# │   └── LEVEL 2: Cart Management

# │       ├── LEVEL 3: Add To Cart

# │       ├── LEVEL 3: Update Cart

# │       ├── LEVEL 3: Remove Package

# │       └── LEVEL 3: Total Price

# ├── LEVEL 1: Feedback & Gallery Module

# │   ├── LEVEL 2: Rating System

# │   │   ├── LEVEL 3: Submit Rating

# │   │   └── LEVEL 3: View Ratings

# │   │

# │   └── LEVEL 2: Gallery System

# │       ├── LEVEL 3: Upload Image

# │       └── LEVEL 3: View Gallery

# ├── LEVEL 1: Query Management Module

# │   └── LEVEL 2: Customer Queries

# │       ├── LEVEL 3: Submit Query

# │       ├── LEVEL 3: Store Query

# │       └── LEVEL 3: Track Query

# ├── LEVEL 1: Admin Module

# │   ├── LEVEL 2: Admin Dashboard

# │   │   └── LEVEL 3: Activity Monitoring

# │   │

# │   ├── LEVEL 2: Package Management

# │   │   ├── LEVEL 3: Add Package

# │   │   ├── LEVEL 3: Update Package

# │   │   └── LEVEL 3: Delete Package

# │   │

# │   └── LEVEL 2: Query Management

# │       ├── LEVEL 3: View Queries

# │       └── LEVEL 3: Mark Resolved

# └── LEVEL 1: Database Module

# ├── LEVEL 2: User Database

# ├── LEVEL 2: Package Database

# ├── LEVEL 2: Booking Database

# └── LEVEL 2: Query Database

# Lab 8: Network Diagram and Critical Path Method (CPM)

## Step 1: Activity Table

| Activity | Description | Duration (Days) | Predecessor |
| --- | --- | --- | --- |
| A | Requirement Gathering | 3 | - |
| B | System Design | 4 | A |
| C | Database Design | 3 | A |
| D | Frontend Development | 8 | B |
| E | Backend Development | 7 | C |
| F | System Integration | 3 | D, E |
| G | Testing | 4 | F |
| H | Deployment | 2 | G |

# Step 2: Network Diagram

A

/   \

B     C

|     |

D     E

\   /

F

|

G

|

H

### Flow Paths

Path 1:
A → B → D → F → G → H

Path 2:
A → C → E → F → G → H

# Step 3: Forward Pass (EST & EFT)

### Formula

EFT = EST + Duration

| Activity | Duration | EST | EFT |
| --- | --- | --- | --- |
| A | 3 | 0 | 3 |
| B | 4 | 3 | 7 |
| C | 3 | 3 | 6 |
| D | 8 | 7 | 15 |
| E | 7 | 6 | 13 |
| F | 3 | 15 | 18 |
| G | 4 | 18 | 22 |
| H | 2 | 22 | 24 |

### Explanation

F starts only after both D and E are completed.

max(15,13) = 15

Therefore:

EST(F) = 15

# Step 4: Backward Pass (LST & LFT)

### Formula

LST = LFT − Duration

| Activity | Duration | LST | LFT |
| --- | --- | --- | --- |
| H | 2 | 22 | 24 |
| G | 4 | 18 | 22 |
| F | 3 | 15 | 18 |
| D | 8 | 7 | 15 |
| E | 7 | 8 | 15 |
| B | 4 | 3 | 7 |
| C | 3 | 5 | 8 |
| A | 3 | 0 | 3 |

# Step 5: Slack Calculation

### Formula

Slack = LST − EST

| Activity | Duration | EST | EFT | LST | LFT | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| A | 3 | 0 | 3 | 0 | 3 | 0 |
| B | 4 | 3 | 7 | 3 | 7 | 0 |
| C | 3 | 3 | 6 | 5 | 8 | 2 |
| D | 8 | 7 | 15 | 7 | 15 | 0 |
| E | 7 | 6 | 13 | 8 | 15 | 2 |
| F | 3 | 15 | 18 | 15 | 18 | 0 |
| G | 4 | 18 | 22 | 18 | 22 | 0 |
| H | 2 | 22 | 24 | 22 | 24 | 0 |

# Step 6: Critical Path

Activities having Slack = 0

A → B → D → F → G → H

### Critical Path Duration

A = 3

B = 4

D = 8

F = 3

G = 4

H = 2

Total Duration = 3 + 4 + 8 + 3 + 4 + 2 = 24 Days

# Final Answer

### Critical Path

A → B → D → F → G → H

### Total Project Completion Time

24 Days

# Lab 9:

# 1. Jira:

# Lab 10:

# 1.Git

# Lab 10:

# Software Cost Estimation using LOC, Function Points, and COCOMO

# Part A – LOC Estimation

## Step 1: Estimated Modules

| Module | Estimated LOC |
| --- | --- |
| Authentication Module (Login/Register) | 1000 |
| Package Management | 2500 |
| Booking & Cart Management | 2000 |
| Rating & Gallery Module | 1200 |
| Query Management | 1000 |
| Admin Dashboard | 1800 |

## Step 2: Calculate Total LOC

Formula:

Total LOC = Σ Module LOC

Calculation:

1000 + 2500 + 2000 + 1200 + 1000 + 1800

Total LOC = 9500

## Step 3: Convert into KLOC

Formula:

KLOC = LOC / 1000

Calculation:

KLOC = 9500 / 1000

KLOC = 9.5

### Result

| Metric | Value |
| --- | --- |
| Total LOC | 9500 |
| KLOC | 9.5 |

# Part B – Function Point Analysis (FPA)

## Step 1: Identify Components

| Component | Count | Weight | Total |
| --- | --- | --- | --- |
| Inputs | 8 | 4 | 32 |
| Outputs | 5 | 5 | 25 |
| Queries | 4 | 4 | 16 |
| Internal Files | 3 | 10 | 30 |
| External Interfaces | 2 | 7 | 14 |

### Explanation

### Inputs

- Customer Registration

- Customer Login

- Admin Login

- Package Booking

- Add to Cart

- Submit Rating

- Upload Image

- Submit Query

### Outputs

- Package List

- Booking Confirmation

- Cart Summary

- Query Status

- Reports

### Queries

- Search Package

- View Booking

- View Gallery

- View Query Status

### Internal Files

- User Database

- Package Database

- Booking Database

### External Interfaces

- Payment Gateway

- MongoDB Atlas Cloud Services

## Step 2: Calculate UFP

Formula:

UFP = Total Inputs + Outputs + Queries + Internal Files + External Interfaces

Calculation:

32 + 25 + 16 + 30 + 14

UFP = 117

## Step 3: Apply VAF

Assume:

VAF = 1.05

Formula:

FP = UFP × VAF

Calculation:

FP = 117 × 1.05

FP = 122.85

FP ≈ 123

### Result

| Metric | Value |
| --- | --- |
| UFP | 117 |
| Final FP | 123 |

# Part C – COCOMO Estimation

## Constants

| Constant | Value |
| --- | --- |
| a | 2.4 |
| b | 1.05 |

## Effort Formula

Effort = a × (KLOC)^b

Substitute Values:

Effort = 2.4 × (9.5)^1.05

Effort ≈ 25.6 Person-Months

### Estimated Effort

≈ 26 Person-Months

# Final Estimation Summary

| Metric | Estimated Value |
| --- | --- |
| LOC | 9500 |
| KLOC | 9.5 |
| Function Points | 123 |
| Estimated Effort | 26 Person-Months |

# Cost Drivers Affecting Estimation

| Cost Driver | Impact |
| --- | --- |
| Team Experience | Experienced developers reduce effort |
| Product Complexity | More features increase development cost |
| Reliability Requirements | Additional testing required |
| Tools & Technology | Modern frameworks improve productivity |
| Schedule Constraints | Tight deadlines increase effort |
| Database Complexity | More data management increases workload |
| Security Requirements | Login and user data protection increase cost |

## Inputs

- Registration

- Customer Login

- Admin Login

- Package Booking

- Add to Cart

- Submit Rating

- Upload Image

- Submit Query

## Outputs

- Package List

- Booking Confirmation

- Cart Details

- Query Status

- Reports

## Queries

- Search Package

- View Booking

- View Gallery

- View Query Status

## Internal Files

- User Database

- Package Database

- Booking Database

## External Interfaces

- Payment Gateway

- MongoDB Atlas

# Task 3 Results

### UFP = 117

### FP = 123

### LOC = 9500

### KLOC = 9.5

# Task 4 Result

Using Basic COCOMO:

Estimated Effort = 26 Person-Months

Lab 11:

1.Git